## MoSCoW Analysis
Library Management System — MoSCoW Prioritisation
Assumption: constrained first release; categories reflect user/stakeholder impact and delivery feasibility. “Won't-Have” means deferred from this release, not permanently rejected.
ID | Requirement | MoSCoW Category | Impact on Users / Stakeholders | Feasibility (Time / Budget / Resources) | Justification
R1 | Search books by title and author | Must-Have | High — users need a fast, reliable way to find books; librarians spend less time handling search requests. | High — a standard catalogue search using title and author fields is straightforward to implement. | Core library functionality with high user impact and low implementation complexity.
R2 | Online book reservation system | Must-Have | High — lets users reserve unavailable or in-demand books remotely and helps librarians manage demand. | Medium to High — requires reservation rules, availability checks, and queue/status handling, but uses the existing catalogue. | A major service requirement that directly improves access to books; feasible within a typical core release.
R3 | Monthly reports on borrowed books for administrators | Should-Have | Medium to High — supports monitoring, planning, and administrative decisions, but is not essential for everyday borrowing. | High — can be generated from borrowing and return transaction records. | Valuable for oversight and planning, but can follow the core search and circulation features if time is limited.
R4 | Email notifications for overdue books | Should-Have | High — reminds users to return books and helps reduce overdue items and manual follow-up. | Medium — needs scheduled checks, email-service integration, message templates, and valid email addresses. | Strong operational benefit, but the system can initially track due dates and overdue status without automated email.
R5 | QR code scanning for borrowing and returning books | Could-Have | Medium — may speed up circulation and reduce manual entry, especially in busy libraries. | Medium — requires QR generation/printing, scanning-capable devices, and workflow testing. | Useful convenience and efficiency improvement, but standard librarian-assisted checkout can support the initial release.
R6 | User-friendly dashboard for librarians | Must-Have | High — gives librarians clear access to book, member, loan, return, and overdue information. | High — a basic dashboard can be built using data and functions already required by the system. | Essential for day-to-day operation and efficient staff use; prioritise a simple dashboard in the first release.
R7 | Allow users to review and rate books | Could-Have | Low to Medium — helps users discover popular books but does not directly enable lending or returns. | Medium — requires review storage, rating calculations, moderation, and abuse prevention. | Adds community value but is not necessary for core library operations.
R8 | Chatbot for user assistance | Could-Have | Medium — can answer common questions and reduce repetitive enquiries. | Low to Medium — quality depends on chatbot design, knowledge content, integration, and ongoing maintenance. | Potentially helpful, but more complex than a searchable FAQ or contact option and can be added later.
R9 | Mobile app version of the system | Won't-Have (initial release) | Medium to High — improves access on phones, but a responsive web interface can serve mobile users initially. | Low to Medium — a separate app adds platform development, testing, deployment, and maintenance costs. | Defer a dedicated mobile app from the current release to protect schedule and budget; reconsider in a future phase. This does not mean permanently rejecting it.
R10 | Multi-language support | Should-Have | Medium to High — makes the system more accessible to users who prefer different languages. | Medium — requires translation of interface text, language selection, and testing across screens. | Important for inclusivity, but can be introduced after the core workflows are stable if resources are constrained.

## MoSCoW Guide
Category | Meaning | How applied here
Must-Have | Essential for the first usable release. | High impact and core to finding books, managing circulation, or operating the system.
Should-Have | Important, but the system can launch without it temporarily. | Provides meaningful operational, administrative, or accessibility benefits.
Could-Have | Desirable if time and budget allow. | Adds convenience or engagement but is not essential to core workflows.
Won't-Have (initial release) | Explicitly deferred from the current scope. | A separate native mobile app is deferred; responsive web access is the suggested interim option.